## Slide 1
ERP TRANSFORMATION STRATEGY
Alpha Manufacturing
Group (AMG)
A Strategic Roadmap to Cloud ERP Migration and Digital Operational Excellence
Prepared by: Jesse Yaw Owusu | June 2026
Notes: Introduce yourself. Say: I was asked to advise AMG on how to replace their legacy ERP system with a modern cloud platform within 12 months without disrupting operations. This presentation walks through my recommended approach.

## Slide 2
THE PROBLEM
AMG's Legacy Systems Are Costing the Business
80%
of custom orders
experienced margin erosion
20+
years old, the age of
AMG's core ERP system
5
siloed systems with
no real-time integration
What is causing this?
The engineering and manufacturing systems share data only once a night through a connection that keeps breaking. When it fails, the factory builds the wrong thing.
No one can see how much profit each order is making until after the work is done and it is too late to fix anything.
Staff use Excel spreadsheets to fill the gaps between systems, creating errors and data that only one person controls.
Notes: Start with the 80% stat. Say: Last year, 80% of AMG's custom orders lost money they should have made. That is not a sales problem or a pricing problem. It is a systems problem. The rest of this slide explains exactly why. For each bullet: explain it in plain language. The nightly sync failure means engineers update designs that the factory never sees. No margin visibility means leadership is flying blind. Excel reliance means critical business data lives on someone's laptop.

## Slide 3
OUR APPROACH
Four Objectives — In Order of Priority
Every decision in this program is measured against these four goals:
01
Fix the BOM Sync
Replace the fragile nightly engineering-to-manufacturing connection with a real-time live integration. This is the most urgent fix. It is losing AMG money every single day.
02
One Source of Truth
Everyone across finance, engineering, and manufacturing sees the same data at the same time. No more conflicting spreadsheets, no more decisions based on outdated information.
03
Controlled Retirement
Switch off the old systems in a planned, step-by-step sequence, not all at once. Each system is only decommissioned after the new one has proven it can replace it.
04
Build Internal Capability
Train AMG's own staff to run the new platform. The goal is independence, not permanent reliance on external consultants.
Notes: Emphasise that these are in priority order — not equal weight. Fixing the BOM sync is so urgent that if the new ERP could only do one thing on day one, that would be it. The rest follow in sequence. If asked why controlled retirement matters: switching everything off at once is like changing the engine of a plane while it is flying. You do it piece by piece.

## Slide 4
PROGRAM PHASES
12-Month Delivery in Three Phases
1
2
3
Foundation
Months 1–3
Purchase and contract the new ERP platform
Define exact project scope and governance structure
Begin cleaning and validating all BOM data
No legacy system switched off yet
Configure & Migrate
Months 4–9
Set up and configure the new ERP to match AMG's processes
Run both old and new systems simultaneously (parallel operations)
Migrate all active orders, live inventory, and open transactions
Connect the engineering system to the new ERP in real-time
Go-Live & Stabilise
Months 10–12
Cut over to the new system only when data is verified
Switch off old systems in a planned sequence
Keep extra technical support on standby for 30 days (hypercare)
Hand full control over to AMG's internal team
Notes: Point at the timeline arrow as you talk. Say: We move left to right — Foundation, then Configure and Migrate, then Go-Live. Each phase has a clear entry and exit point. The most important phase to explain is Phase 2. Parallel operations means both systems run at the same time. Staff enter data into both. We compare the outputs. Only when the new system's numbers match the old system's numbers do we switch over. It is the safety net that prevents a disaster. Hypercare in Phase 3 means: extra technical support on standby around the clock for the first 30 days after go-live, in case anything breaks.

## Slide 5
RISK MANAGEMENT
Top 4 Risks and How We Manage Them
BOM Data Quality
HIGH
If we migrate inaccurate product data into the new system, we reproduce the same manufacturing problems we are trying to solve.
Mitigation: Dedicate a full data cleansing workstream in Phase 1. Every BOM record is validated before migration begins. Bad data does not move forward.
Scope Creep
HIGH
People keep adding new requirements after the project starts. Each addition seems small but together they push the deadline out and inflate costs.
Mitigation: Formal change control process from day one. Any new requirement must be submitted, evaluated, and approved by the executive team before it is added.
Cutover Disruption
MED
Switching systems while active customer orders are in progress risks errors on work already underway.
Mitigation: Plan go-live during AMG's lowest-volume period. Run parallel operations for at least 4 weeks before fully switching off the old system.
User Adoption
MED
Employees revert to Excel out of habit. The new system exists but nobody trusts it — so the data quality problem never gets solved.
Mitigation: Structured training and change management treated as a formal project workstream, not an afterthought added at the end.
Notes: For each risk, say the consequence first before the mitigation. The consequence is what makes the risk real. BOM quality: if we move bad product data into the new system, the factory still builds the wrong thing. We have just moved the problem to a more expensive location. Scope creep: the number one reason ERP projects run over time and over budget. Every yes to a new requirement is a no to the deadline. User adoption: you can build the most perfect system in the world, but if people keep using Excel instead, the transformation has failed.

## Slide 6
SCOPE & SEQUENCING
What Goes Live on Day 1 vs. What Gets Deferred
DAY 1 MUST-HAVES
Core Financials — Record all money in and out from day one (general ledger, payables, receivables)
Manufacturing and MRP — Calculate what materials to order and when based on live production
Procurement — Raise and track purchase orders to suppliers
Real-time BOM Integration — Replace the broken nightly sync with a live engineering connection
DELIBERATE DEFERRALS
CRM Integration — The factory can operate without the sales system being connected on launch day
Advanced Reports and Dashboards — Only build reports after one full quarter of clean, reliable data is flowing through the new system
HR and Payroll Migration — Payroll errors have legal consequences. This runs as a separate, careful workstream after the core ERP is stable
Notes: The key message on this slide is that deferring things is not failure — it is discipline. Trying to launch everything at once is what causes ERP projects to collapse. On the dashboards deferral: explain it this way. If you build reports on top of data that is still settling after a major system change, the reports will show the wrong numbers. Leadership will lose trust in the new system. Wait one quarter, get clean data, then build the reports. On payroll: getting payroll wrong means employees are not paid correctly. That is a legal and HR problem on top of a technology problem. Defer it.

## Slide 7
CUSTOMISATION DISCIPLINE
The Rule That Protects
the Entire Program
Configure the business to fit the software, not the other way around.
Modern ERP platforms are built on industry best practices. In most cases, the standard process is actually better than what AMG does today.
Every customisation adds cost, extends testing time, and makes future upgrades harder. The answer to any customisation request is NO by default.
If a genuine exception is needed, it must go through formal executive approval with a documented business justification.
Notes: This slide sometimes surprises executives. They expect to mould the software to exactly how they work today. Explain why that is a trap. Analogy: when you move into a new house, you adapt how you live to the layout of the house. You do not knock down walls to recreate your old house inside the new one. Same principle here. If they push back and say their processes are unique: acknowledge it, but point out that AMG's current processes produced 80% margin erosion. The standard process probably cannot do worse.

## Slide 8
DATA & REPORTING CONTINUITY
Leadership Never Loses Visibility During the Transition
What Data Do We Move?
Move only what is currently active: live orders, outstanding invoices, current inventory levels, open purchase orders
Historical data older than 3 years goes into a read-only archive — still accessible if needed, but not cluttering the new system
Avoid the common mistake of migrating 20 years of messy records into a clean new platform
Who Reports What and When?
During parallel operations, all reports still come from the old system
We only switch reporting to the new system after both systems show matching numbers
Every critical KPI — margin per order, order backlog, labour cost — has a named person responsible for it throughout the transition
Protecting Month-End Close
Go-live is planned away from any month-end, quarter-end, or year-end close period
The first close on the new system is treated as a practice run with extra time and additional finance support
No finance team is forced to close the books on an unfamiliar system under deadline pressure
Notes: KPI means Key Performance Indicators — the specific numbers leadership checks to know if the business is healthy. For AMG the three most important are: contribution margin per order (are we making money on each job?), order backlog (how much work is coming?), and labour utilisation (are our people productive?). On month-end close: explain it simply. At the end of every month, the finance team reconciles all transactions and produces reports for leadership. It is already stressful under normal conditions. Doing it for the first time on a brand new system with a hard deadline is a recipe for errors. We avoid that by planning the go-live for the middle of a month.

## Slide 9
PRINCIPLES FOR SUCCESS
Three Things That Will Make or Break This Program
1
Data Before Everything
A new system built on bad data produces bad outcomes faster than the old one. Before any migration begins, AMG's data, especially the Bill of Materials, must be cleaned, validated, and verified. This is the foundation the entire transformation is built on.
2
Parallel Operations Are Non-Negotiable
Running old and new systems simultaneously during Phase 2 is the safety net that prevents a failed cutover from becoming a business crisis. We do not switch off the old system until the new system has proven it can replace it with verified data.
3
People Adoption Determines ROI
The return on this investment is only realised if employees actually use the new system. Technology transformations fail most often because of people, not technology. Structured training and change management are not afterthoughts, they are as important as the technical implementation itself.
Notes: These three principles are what you come back to if an interviewer challenges any part of your strategy. Principle 1 — if they ask why Phase 1 takes 3 months: because cleaning 20 years of data takes time. Rushing it means moving bad data into the new system. Principle 2 — if they ask why parallel operations: because AMG cannot afford to find out the new system has problems after the old one is already switched off. Principle 3 — if they ask what the biggest risk is: it is not technical. It is whether AMG's 200 employees will actually use the new system or go back to Excel. That is what determines whether this transformation delivers value or just costs money.

## Slide 10
CONCLUSION
The cost of inaction is higher
than the cost of transformation
AMG's margin erosion is compounding. Every month the legacy systems remain in place, the problem grows harder and more expensive to fix.
A phased, 12-month program protects operations while driving the transformation forward
Disciplined scope control and a no-customisation default keeps the program on time and on budget
A data-first approach ensures the new system is built on a clean, verified foundation
Structured change management ensures people adopt the system and the investment delivers real value
Executive commitment is the single most important factor, the project team cannot succeed without it
Jesse Yaw Owusu | June 2026 | AMG ERP Transformation Strategy
Notes: Close by bringing everything back to the 80% figure from slide 2. Say: We started with the fact that 80% of AMG's custom orders lost money last year. That number is not going to fix itself. The longer AMG waits, the more it costs to unwind 20 years of fragmented systems. The last bullet is the most important point to land. Say it directly: the technology is the easy part. What will determine whether this program succeeds or fails is whether the executive team holds the line on scope, supports the change management process, and stays committed when the program hits its difficult moments — and every transformation program hits difficult moments. Then open to questions.